SERVICE PROPOSAL

Dismantling, Rigging & Export Packing

Plant 35 + Reclaim Line  ·  Hillsville, Virginia, USA

| SUBMITTED BY | Eastern Ghats International Pte Ltd |
| --- | --- |
| SUBMITTED TO | Parkdale USA |
| PROJECT SITE | Plant 35 + Reclaim Line, Hillsville, Virginia, USA |
| PROPOSAL DATE | April 1, 2026 |
| VALIDITY | 30 Days from Proposal Date |

1.  Introduction & Company Overview

Eastern Ghats International Pte Ltd (EGIPL) is a Singapore-registered machinery trading and rigging services company with extensive experience in the dismantling, packing, and international relocation of industrial textile machinery. We have successfully executed large-scale rigging operations across the United States, Europe, and Asia, with a proven track record in handling precision spinning and preparatory equipment.

We are pleased to submit this formal proposal to Parkdale USA for the complete dismantling, rigging, and export-packing of machinery at Plant 35 and the Reclaim Line, located at Hillsville, Virginia, USA.

2.  Project Overview

| Project Name | Plant 35 + Reclaim Line — Dismantling & Rigging |
| --- | --- |
| Project Location | Hillsville, Virginia, USA |
| Client / Counterparty | Parkdale USA |
| Service Provider | Eastern Ghats International Pte Ltd |
| Total Scope | Dismantling, Packing & Loading of all machinery per Annexure |
| Project Duration | 3 – 4 Months from commencement |
| Total Rigging Cost | USD 320,000 (Three Hundred Twenty Thousand US Dollars) |

3.  Scope of Work

EGIPL will provide a fully managed rigging service covering the following activities:

- Professional dismantling of all machinery listed in Annexure 1 (Plant 35) and Annexure 2 (Reclaim Line)

- Supply of all packing materials including timber crating, foam, stretch wrap, and moisture-barrier protection

- Forklift operations and internal plant movement of dismantled equipment

- Sequential loading onto transport vehicles / containers for export

- Labelling and tagging of all components for easy reassembly at destination

- Coordination with on-site plant management to ensure minimal disruption

- Final site clean-up and handover documentation

Inclusions: All labour, wood, packing materials, and forklift charges are included in the quoted price.

Exclusions: International freight, customs duties, insurance, and civil / electrical disconnection works are not included unless separately agreed.

4.  Annexure 1 — Plant 35 Machinery (Rieter Cards & Drawframes)

The following Rieter machinery at Plant 35, Hillsville, VA is included in the rigging scope:

| Manufacturer | Machine / Model | Serial No. |
| --- | --- | --- |
| Rieter | Card C80 #1 | 40028508-00183 |
| Rieter | Card C80 #2 | 40028508-00182 |
| Rieter | Card C80 #3 | 40028508-00181 |
| Rieter | Card C80 #4 | 40028508-00180 |
| Rieter | Card C80 #5 | 40028508-00179 |
| Rieter | Card C80 #6 | 40028508-00178 |
| Rieter | Card C80 #7 | 40028508-00177 |
| Rieter | Card C80 #8 | 40028508-00176 |
| Rieter | Card C80 #9 | 40028508-175 |
| Rieter | Card C80 #10 | 40028508-174 |
| Rieter | Card C80 #11 | 40028508-173 |
| Rieter | Card C80 #12 | 40028508-172 |
| Rieter | RBS D50 Drawframe #1 | 40027519-1 |
| Rieter | RBS D50 Drawframe #2 | 40027519-13 |
| Rieter | RBS D50 Drawframe #3 | 40027519-12 |
| Rieter | RBS D50 Drawframe #4 | 40027519-11 |
| Rieter | RBS D50 Drawframe #5 | 40027519-10 |
| Rieter | RBS D50 Drawframe #6 | 40027519-5 |
| Rieter | RBS D50 Drawframe #7 | 40027519-4 |
| Rieter | RBS D50 Drawframe #8 | 40027519-3 |
| Rieter | RBS D50 Drawframe #9 | 40027519-2 |
| Rieter | RBS D50 Drawframe #10 | 40027519-9 |
| Rieter | RBS D50 Drawframe #11 | 40027519-8 |
| Rieter | RBS D50 Drawframe #12 | 40027519-7 |
| Rieter | RBS D50 Drawframe #13 | 40027519-6 |

Additional Plant 35 Equipment (Annexure 1):

- 2 x Blend Line

- 4 x As Waste Hopper

- 2 x CL-U

- 2 x CL-P

- 4 x BO-P

- 7 x FD-S

- 2 x MPM Mixer

- 7 x MX-U

- 4 x BR-ASU

- 1 x LVSA

- 1 x MPM 10 Cell

- 3 x Control Panels

- 12 x C80 Rieter Cards

- 13 x Rieter SBD-50 Finishers

5.  Annexure 2 — Reclaim Line Machinery

The following reclaim line equipment (Trutzschler, MSI, MSL & MPM) is included in the rigging scope:

| Manufacturer | Machine / Model | Serial No. |
| --- | --- | --- |
| Trutzschler | Bale Opener B/O 1600 | TR1076998/C12665-01 |
| Trutzschler | Cleanomat CVT3/1600 | 139367 A |
| Trutzschler | Cleanomat CVT3/1600 | 139366 A |
| Trutzschler | Continental Bale Press | 1832 |
| Trutzschler | Continental Baler #1 | 242327X54 |
| Trutzschler | Dustex DX | R 00000/C 12683-02 |
| Trutzschler | Dustex DX/1600 | R10785/C 12682-01 |
| Trutzschler | LVSA Condenser | R 10779/C 12674-02 |
| Trutzschler | LVSA Condenser | R 10763/C 12660-01 |
| MSI | MSI Baler #W7-M | — |
| MSI | MSI VB6030HD Baler | — |
| Trutzschler | Tuftomat TFV1/1600 | 139365 |
| — | Wiema Briquetter (x2) | — |
| — | Continental Baler Rebuilt | — |
| ILE | Fiber Compactor (x4) | — |
| MSL | Trutzschler MSL | C18301-01 |
| MPM 97 | 8 Cell MPM | C12673-01 |

6.  Commercial Terms & Pricing

| Description | Amount (USD) |
| --- | --- |
| Dismantling, Packing & Loading — Plant 35 + Reclaim Line (Lump Sum) | USD 320,000 |
| Packing Materials (Wood, Foam, Stretch Wrap) — INCLUDED | Included |
| Forklift & Internal Plant Movement — INCLUDED | Included |
| TOTAL RIGGING COST (ALL INCLUSIVE) | USD 320,000 |

Payment Terms: To be mutually agreed upon contract execution.

Currency: All amounts in United States Dollars (USD).

7.  Project Timeline

| # | Phase | Details |
| --- | --- | --- |
| 1 | Mobilisation & Site Survey | EGIPL team mobilises to Hillsville; site survey, safety induction, and work plan finalisation |
| 2 | Disconnection & Preparation | Coordination with client's electrical / civil team for service disconnection prior to rigging commencement |
| 3 | Dismantling — Reclaim Line | Systematic dismantling of Trutzschler, MSI, MSL & MPM reclaim line equipment |
| 4 | Dismantling — Plant 35 | Dismantling of Rieter C80 Cards, RBS D50 Drawframes, and all ancillary equipment |
| 5 | Packing & Crating | All components packed, crated, labelled, and prepared for outbound loading |
| 6 | Loading & Completion | Final loading onto transport vehicles; handover documentation and site clearance |

Estimated Total Duration: 3 – 4 months from commencement date, subject to site access and client coordination.

8.  Terms & Conditions

- This proposal is valid for 30 days from the date of issue.

- The quoted price is lump sum and covers the full scope as described. Any additional machinery or scope changes will be priced separately.

- Client to ensure all utilities (electricity, compressed air) are operational until the day before dismantling of each machine.

- Client to provide safe, unobstructed access to all machinery during the project duration.

- EGIPL will comply with all applicable US federal, Virginia state, and site-specific health, safety, and environmental regulations.

- Ownership and title of machinery remains with the client until full payment is received.

- This proposal does not include international freight, marine insurance, import duties, or customs brokerage.

9.  Acceptance & Signature

Should this proposal be acceptable, please sign and return a copy as confirmation of your acceptance. Upon receipt, EGIPL will proceed to issue a formal service agreement for execution.

| FOR PARKDALE USA | FOR EASTERN GHATS INTERNATIONAL PTE LTD |
| --- | --- |
| Authorised Signatory Name & Designation: ___________________ Date: ________________________________ | Suresh Appiya Radhakrishnan Legal Representative / Authorised Signatory Date: ________________________________ |

Eastern Ghats International Pte Ltd  |  Singapore  |  www.texcoms.com